## Summary
Development Efforts
[6 empty] | Sr No | Task | Deliverable | Effort (PD)
[6 empty] | 1 | Development | Data Integration | 1216.875
[6 empty] | Total (CUT) |  |  | 1216.875
65%
20
Sr No | Activity | Deliverable | Ratio% | Effort (PD) | Effort (PM)
1 | Assessment | Data Integration & Data Migration Code | 6% | 112.3269 | 5.6163
2 | Design | Requirement Analysis, architecture, solution design and data modeling | 16% | 299.5385 | 14.9769
3 | Development | Data Integration & Data Migration Code | 65% | 1216.875 | 60.8438
4 | Pre-Prod Support | Support to testing (SIT & UAT), Production Implementation | 10% | 187.2115 | 9.3606
5 | Warranty Support | Post Production Support | 3% | 56.1635 | 2.8082
Total Efforts |  |  | 100% | 1759.7885 | 87.9894
Note on O6: Anand: CUT Ratio %

## Splunk Estimates
| Activity | Task | Sub Task | Efforts | Simple | Medium | Complex | Owner
1 | Splunk Setup | Forwarder Installation | Agent Installation on all the application Servers. | 1-2 weeks | 70% | 20% | 10% | Approval and Support from Application and network Team/Splunk Admin
2 | Data-Onboarding | Data and indices created into the System (Operational) | Minimum of 5 data sets ingestion and normalised expected. Firewall, Network and Endpoint (Windows) (Apps available in Splunk Library) Anticipated activities for this task are: |  |  |  |  | Splunk Team/Infra Team
|  |  | Creation of indices | 1 week | 70% | 20% | 10%
|  |  | Normalising the data | 1-2 weeks | 70% | 20% | 10%
|  |  | Field extraction based on the business specification (Apps available in Splunk Library) | 1-2 weeks | 70% | 20% | 10%
|  |  | Ingestions pattern advice based | 1-2 weeks | 70% | 20% | 10%
3 | Integrations | Integrations in the systems working as per the specifications articulated by users (Operational) | Anticipated integrations tasks are - Minimum of 5 integration expected with code base handed over and transitioned into the RTB Team (See below detail)
|  |  | Integration with Databases via DB Connect (App available for Hadoop, Incident management(ServiceNow) for two way Integration) | 2 weeks | 60% | 20% | 20% | Splunk Admin/Developer Team/Database Team
4 | Dashboard Creation | Dashboards in the systems working as per the specifications articulated by users (Operational) | Build of 10+ Dashboards to support (Considering Dashboards+Alert+Reports) | 4-6 weeks | 40% | 30% | 30% | Splunk Developer
|  |  | Support monitoring of data feeds | 1-2 weeks | 70% | 20% | 10% | Splunk Developer
5 | Data Reconciliation | Document with a plan | Reconcile data for 3 main ingested data sets from Firewall and Endpoint (Windows desktop events) | 2 weeks | 60% | 20% | 20% | Splunk Admin/Developer Team
|  | Document with Hosts reconciled against the original expected | Delivery of a plan of work with internal infrastructure teams to reconcile data coming from our estate e.g. Reconcile hosts from Firewall | 2 weeks | 60% | 20% | 20% | Splunk Admin/Developer Team
|  |  | Delivery of reconciled hosts from those data sets | 2 weeks | 60% | 20% | 20% | Splunk Admin/Developer Team
6 | Metadata extraction | Document/Knowledge Base article with the Metadata and their definitions | Creation of an internal knowledge base of the metadata ingested into the Splunk tool | 2 weeks | 60% | 20% | 20% | Splunk Developer
7 | Splunk ES | Document/Knowledge Base article with the ES best practices | Splunk ES best practise for data utilisation | Need splunk professional advice |  |  |  | Splunk Developer/ Splunk Professional

## Estimates - Big Data
Type |  | Source Table/ File Count | Simple | Medium | Complex | Effort (PD)
Re-Usable Component | Audit/reconciliation framework |  |  |  |  | 40
| Metadata Registration Framework |  |  |  |  | 30 | Unit Efforts
| De-Duplicate Check Framework |  |  |  |  | 20 | Efforts in Person hours
| Data Quality Check Framework |  |  |  |  | 30 | Activities | Simple | Medium | Complex
| Total |  |  |  |  | 120 | Steps
BDDL (File System) | Landing to Raw Layer (Stage) | 400 | 70% | 20% | 10% |  | Ingesting raw data using ELF from Landing Area | 1 | 2 | 3
| Ingesting raw data |  | 35 | 20 | 15 | 70 | Batch - Transform | 4 | 6 | 8
| Process Metadata Registration Framework |  | 35 | 20 | 12.5 | 67.5 | Process Metadata Registration Framework | 1 | 2 | 2.5
| Process DQ Check |  | 35 | 10 | 5 | 50 | Process DQ Check | 1 | 1 | 1
| Scheduling |  | 35 | 10 | 5 | 50 | Scheduling | 1 | 1 | 1
| Sub Total |  | 140 | 60 | 37.5 | 237.5 | Process De-Duplicate Check | 1 | 1 | 1
| Raw Layer (Stage) to Refined Layer (CSA) | 400 | 40% | 30% | 30% |  | Load tables to Consumption | 1 | 1 | 1
| Process De-Duplicate Check Framework |  | 20 | 15 | 15 | 50 | Export LRT using Sqoop/Spark | 1 | 2 | 3
| Batch processing- Apply transformation logic |  | 80 | 90 | 120 | 290 | Spark Transformation job to Data Mart | 2 | 4 | 6
| Process DQ Check |  | 20 | 15 | 15 | 50 | Call Data Encryption API | 1 | 1.5 | 2
| Process Data Encryption |  | 20 | 22.5 | 30 | 72.5
| Scheduling |  | 20 | 15 | 15 | 50
| Sub Total |  | 160 | 157.5 | 195 | 512.5
| Refined Layer to Data Mart | 350 | 50% | 30% | 20%
| Export final Refined layer to Data Mart |  | 21.875 | 26.25 | 26.25 | 74.375
| Transformation |  | 43.75 | 52.5 | 52.5 | 148.75
| Scheduling |  | 21.875 | 13.125 | 8.75 | 43.75
| Total |  |  |  |  | 266.875
Common | Data Modelling |  |  |  |  | 40
| Cluster Setup |  |  |  |  | 20
| Setup Authentication using Kerberos |  |  |  |  | 10
| Setup ACL |  |  |  |  | 10
| Total |  |  |  |  | 1216.875

## Estimation (hidden)
Type |  | Source Table/File Count | Simple | Medium | Complex | Total PD
Re-Usable | Framework Development | [7 empty] | Unit Efforts
| Audit/reconciliation framework |  |  |  |  | 50 | 30/40 |  | Efforts in Person hours
| Metadata Registration Framework |  |  |  |  | 50 | metadata registration framework |  | Activities | Simple | Medium | Complex
| De-Duplicate Check Framework |  |  |  |  | 40 |  |  | Database
| Basic DQ check Framework |  |  |  |  | 40 |  |  | Source Connectivity And Ingestion | 6 | 8 | 10
[7 empty] | data completeness check | 30/40
| Total |  |  |  |  | 180 |  |  | Call for Hive Table DDL Creation Framework | 3 | 4 | 5
E Coupon (RDBMS) | Raw Layer | 31 | 100% | 0% | 0% |  |  |  | Call for Basic DQ Check Framework | 2 | 2 | 2
| Source Connectivity And Ingestion |  | 23.25 | 0 | 0 | 23.25 | Ingesting raw data using elf |  | Scheduling | 2 | 2 | 2
| Create table metadata sheet for Hive and call DDL Creation utility |  | 11.625 | 0 | 0 | 11.625 |  |  | File System
| Basic DQ Check Framework |  | 7.75 | 0 | 0 | 7.75 |  |  | File system Connectivity And Ingestion | 2 | 4 | 6
| Scheduling |  | 7.75 | 0 | 0 | 7.75 |  |  | Call for Hive Table DDL Creation Framework | 1 | 1 | 1
| Total |  |  |  |  | 50.375 |  |  | Call for Basic DQ Check Framework | 1 | 1 | 1
| Harmonized Layer | 28 | 100% | 0% | 0% |  |  |  | Scheduling | 1 | 1 | 1
| Hive Table DDL Creation |  | 7 | 0 | 0 | 7 |  |  | Harmonized Layer
| Lookup &Transform |  | 21 | 0 | 0 | 21 |  |  | Call for Hive Table DDL Creation Framework | 2 | 4 | 6
| CDC framework |  | 21 | 0 | 0 | 21 |  |  | Lookup &Transform | 6 | 10 | 14
| Business Rule |  | 21 | 0 | 0 | 21 |  |  | CDC framework | 6 | 10 | 14
| Scheduling |  | 7 | 0 | 0 | 7 |  |  | Business Rule | 6 | 12 | 16
| Total |  |  |  |  | 77 |  |  | Scheduling | 2 | 2 | 2
| Semantic Layer | 21 | 75% | 25% | 0% |  |  |  | Common
| Sqoop export of ORT to Teradata tables |  | 7.875 | 3.9375 | 0 | 11.8125 |  |  | Sqoop export of ORT to Teradata tables | 4 | 6 | 8
| Sqoop export of final LRF tables to Teradata tables |  | 15.75 | 7.875 | 0 | 23.625 |  |  | Sqoop export of final LRF tables to Teradata tables | 8 | 12 | 16
| Total |  |  |  |  | 35.4375
IVR (RDBMS) | Raw Layer | 6 | 100% | 0% | 0%
| Source Connectivity And Ingestion |  | 4.5 | 0 | 0 | 4.5
| Create table metadata sheet for Hive and call DDL Creation utility |  | 2.25 | 0 | 0 | 2.25
| Basic DQ Check Framework |  | 1.5 | 0 | 0 | 1.5
| Scheduling |  | 1.5 | 0 | 0 | 1.5
| Total |  |  |  |  | 9.75
| Harmonized Layer | 9 | 100% | 0% | 0%
| Hive Table DDL Creation |  | 2.25 | 0 | 0 | 2.25
| Lookup &Transform |  | 6.75 | 0 | 0 | 6.75
| CDC framework |  | 6.75 | 0 | 0 | 6.75
| Business Rule |  | 6.75 | 0 | 0 | 6.75
| Scheduling |  | 2.25 | 0 | 0 | 2.25
| Total |  |  |  |  | 24.75
| Semantic Layer | 6 | 80% | 20% | 0%
| Sqoop export of ORT to Teradata tables |  | 2.4 | 0.9 | 0 | 3.3
| Sqoop export of final LRF tables to Teradata tables |  | 4.8 | 1.8 | 0 | 6.6
| Total |  |  |  |  | 9.9
AML-KYC (File System) | Raw Layer | 141 | 100% | 0% | 0%
| File system Connectivity And Ingestion |  | 35.25 | 0 | 0 | 35.25
| Create table metadata sheet for Hive and call DDL Creation utility |  | 17.625 | 0 | 0 | 17.625
| Basic DQ Check Framework |  | 17.625 | 0 | 0 | 17.625
| Scheduling |  | 17.625 | 0 | 0 | 17.625
| Total |  |  |  |  | 88.125
| Harmonized Layer | 124 | 100% | 0% | 0%
| Hive Table DDL Creation |  | 31 | 0 | 0 | 31
| Lookup &Transform |  | 93 | 0 | 0 | 93
| CDC framework |  | 93 | 0 | 0 | 93
| Business Rule |  | 93 | 0 | 0 | 93
| Scheduling |  | 31 | 0 | 0 | 31
| Total |  |  |  |  | 341
| Semantic Layer | 8 | 100% | 0% | 0%
| Sqoop export of ORT to Teradata tables |  | 4 | 0 | 0 | 4
| Sqoop export of final LRF tables to Teradata tables |  | 8 | 0 | 0 | 8
| Total |  |  |  |  | 12
Common | Surrogate Key generation * |  |  |  |  | 50
| Data Security : Table level access matrix set up. |  |  |  |  | 50
| Data Modeling |  |  |  |  | 40
| UAT Support Activity(1 resource for 4 weeks) |  |  |  |  | 20
| Deployment and warranty support (1 resource for 6 weeks) |  |  |  |  | 30
| SIT Support(1 resource for 4 weeks) |  |  |  |  | 20
| Total |  |  |  |  | 1038.3375
Legend
This line item needs further clarity.

## Assumptions (hidden)
Assumptions
1 | There is no real-time data processing required. All loads are batch only.
2 | Data from all the sources supports / implemented in ASCII.
3 | Simple, Medium, Complex calculation is based on the data provided by the VPoC team.
4 | There is no historical data migration required (Full File will contain entire data and will be Truncate & Load).
5 | All data from source is in English language
6 | Basic audit functionality have to be done. (Row count check from source with Harmonized Layer count)
7 | Line item estimation of common component (surrogate key generation) is assumed to be simple to medium complexity. But it needs to be revisited for clarity.
8 | Existing Bigdata infrastucture will be used.
9 | The estimates does not cover any infrastructure cost and efforts and server setup.
10 | All files will be available on shared landing zone will be used for ingestion.
11 | Big data distribution to be used will be Hortonworks.
Out of Scope
1 | Data Governance activities like data classification, profiling.
2 | IVR, AML-KYC and E-Coupon are the data sources considered for current estimations. All other data sources is out of scope.
3 | Push from Inbound sources
4 | Estimates only cover unit testing effort , any end to end testing and comparison with previous state is out of scope (BiSquad team will be able to provide for end to end testing)
5 | DBA, Administration, Hardware and Software configuration along with any type of capacity planning
6 | Hortonworks Cluster installation and configuration

## Assumptions and Dependencies
SL No. | Assumptions and Dependancies
1 | Data ingestion from landing to HDFS staging layer will be one to one
2 | Standard Metadata registration framework will be developed.
3 | Data loaded from CSA to Data Marts will be simple.
4 | 400 tables from the sources will be available in landing layer.
5 | Data from all the sources will be implemented in ASCII
6 | Simple, Medium, Complex calculation is based on the discussion with IDFC team.
7 | Consumption layer will roughly comprise of 285 tables after transformation.
8 | Basic data quality check will be in scope.
9 | Data archival is currently out of scope.
10 | Basic audit functionality have to be done.
11 | Bigdata infrastucture will be setup.
12 | The estimates does not cover any infrastructure cost and efforts and server setup.
13 | Existing business rules/transformations will be used. Any additional changes is not covered in estimates.
14 | Timely access to relevant information, documentation, systems and applications.
15 | NFRs such as performance and SLAs will be collected during the requirements gathering phase.
16 | The total effort does not include any license cost of any tools which are not of existing technology stack.
17 | No unstructured data is part of the source system.
18 | Changes to requirements identified after “Assessment” phase would lead to re-estimate and come up with revised milestones.
19 | Any SW licenses will be procured by IDFC and be made available to Cognizant team

## Scope
In Scope
400 files ingestion to BDDL from Landing layer
Basic data quality check, Audit/Reconciliation framework and Metadata Registration Framework.
Deployment validation scripts will be developed
285 Load ready tables to offload into DataMart
Cluster Installation and Configuration.
Setting up kerberos
Data Encryption
Setting up ACL
Calling existing Data Masking API
Cluster Sizing
Data Modelling of Staging and CSA Layer.
Out of Scope
Any other sources not mentioned in the Scope document.
Data Archival
History Data Migration
Any infrastructure setup for SIT, UAT and production environment
Code promotion across any environment
Software license procurement, software installation and administration activities for SIT, UAT and Production environment
Handling of data quality issues within source systems
Addition of any new functionality to current applications
Fixing any existing data issues in the current applications
Changes to any of the current data sources interfaces and data feeds
Data Masking